## 1
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
81 | dimension check for the material control of door installation | door frame | door frames | each batch | tape measure | blank | door/window
85 | dimension check for the material control of door installation | hardwood solid core flush door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
86 | thickness check for the material control of door installation | hardwood solid core flush door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
88 | dimension check for the material control of door installation | timber door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
89 | thickness check for the material control of door installation | timber door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
91 | dimension check for the material control of door installation | non-frp timber door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
92 | thickness check for the material control of door installation | non-frp timber door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
94 | dimension check for the material control of door installation | frp timber door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
95 | thickness check for the material control of door installation | frp timber door | hardwood solid core flush doors | each batch | tape measure | blank | door/window
141 | measure dimension for aluminum extruded section include ironmongery | handle | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
142 | measure dimension for aluminum extruded section include ironmongery | hinge | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
143 | measure dimension for aluminum extruded section include ironmongery | latch | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
144 | measure dimension for aluminum extruded section include ironmongery | door ironmongery | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
145 | measure dimension for aluminum extruded section include ironmongery | locks | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
146 | measure dimension for aluminum extruded section include ironmongery | door slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
147 | measure dimension for aluminum extruded section include ironmongery | drawer slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | tape measure | blank | door/window
157 | measure dimension for glass | glass panel | glass | each batch | tape measure | blank | door/window

## 2
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
83 | visual surface check for the material control of door installation | door frame | door frames | each batch | N/A | blank | door/window
84 | visual surface check for the material control of door installation | hardwood solid core flush door | hardwood solid core flush doors | each batch | N/A | blank | door/window
87 | visual surface check for the material control of door installation | timber door | hardwood solid core flush doors | each batch | N/A | blank | door/window
90 | visual surface check for the material control of door installation | non-frp timber door | hardwood solid core flush doors | each batch | N/A | blank | door/window
93 | visual surface check for the material control of door installation | frp timber door | hardwood solid core flush doors | each batch | N/A | blank | door/window
120 | review sample for aluminum extruded section include ironmongery | handle | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
121 | review sample for aluminum extruded section include ironmongery | hinge | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
122 | review sample for aluminum extruded section include ironmongery | latch | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
123 | review sample for aluminum extruded section include ironmongery | door ironmongery | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
124 | review sample for aluminum extruded section include ironmongery | locks | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
125 | review sample for aluminum extruded section include ironmongery | door slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
126 | review sample for aluminum extruded section include ironmongery | drawer slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
134 | visual inspection for aluminum extruded section include ironmongery | handle | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
135 | visual inspection for aluminum extruded section include ironmongery | hinge | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
136 | visual inspection for aluminum extruded section include ironmongery | latch | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
137 | visual inspection for aluminum extruded section include ironmongery | door ironmongery | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
138 | visual inspection for aluminum extruded section include ironmongery | locks | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
139 | visual inspection for aluminum extruded section include ironmongery | door slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
140 | visual inspection for aluminum extruded section include ironmongery | drawer slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | N/A | blank | door/window
155 | review sample for glass | glass panel | glass | each batch | N/A | blank | door/window
156 | visual inspection for glass | glass panel | glass | each batch | N/A | blank | door/window
159 | visual inspection for setting blocks, edge blocks, spacers and shims during window installation | spacer | setting blocks, edge blocks, spacers and shims | each batch | N/A | blank | door/window
160 | visual inspection for setting blocks, edge blocks, spacers and shims during window installation | setting blocks | setting blocks, edge blocks, spacers and shims | each batch | N/A | blank | door/window
161 | visual inspection for setting blocks, edge blocks, spacers and shims during window installation | edge block | setting blocks, edge blocks, spacers and shims | each batch | N/A | blank | door/window
162 | visual inspection for setting blocks, edge blocks, spacers and shims during window installation | shim | setting blocks, edge blocks, spacers and shims | each batch | N/A | blank | door/window
163 | visual inspection for gaskets and weatherstrips | gasket | gaskets and weatherstrips | each batch | N/A | blank | door/window
164 | visual inspection for gaskets and weatherstrips | weatherstrip | gaskets and weatherstrips | each batch | N/A | blank | door/window
165 | visual inspection for sealants | structual sealant | sealants | each batch | N/A | qc inspector (factory) | door/window
166 | visual inspection for sealants | weather sealants | sealants | each batch | N/A | qc inspector (factory) | door/window

## 3
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
148 | 2mm thickness check for aluminum extruded section include ironmongery | handle | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
149 | 2mm thickness check for aluminum extruded section include ironmongery | hinge | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
150 | 2mm thickness check for aluminum extruded section include ironmongery | latch | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
151 | 2mm thickness check for aluminum extruded section include ironmongery | door ironmongery | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
152 | 2mm thickness check for aluminum extruded section include ironmongery | locks | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
153 | 2mm thickness check for aluminum extruded section include ironmongery | door slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
154 | 2mm thickness check for aluminum extruded section include ironmongery | drawer slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | digital vernier scale | blank | door/window
158 | thickness check for glass | glass panel | glass | each batch | digital vernier scale | blank | door/window

## 4
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
82 | brand name check for the material control of door installation | door frame | door frames | each batch | bill of materials | blank | door/window
127 | brand name check for aluminum extruded section include ironmongery | hinge | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
128 | brand name check for aluminum extruded section include ironmongery | handle | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
129 | brand name check for aluminum extruded section include ironmongery | latch | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
130 | brand name check for aluminum extruded section include ironmongery | door ironmongery | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
131 | brand name check for aluminum extruded section include ironmongery | locks | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
132 | brand name check for aluminum extruded section include ironmongery | door slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
133 | brand name check for aluminum extruded section include ironmongery | drawer slides | aluminum extruded section include ironmongery (hinge, handle and latches) | each batch | bill of materials | blank | door/window
167 | brand name check for sealants | structual sealant | sealants | each batch | bill of materials | qc inspector (factory) | door/window
168 | brand name check for sealants | weather sealants | sealants | each batch | bill of materials | qc inspector (factory) | door/window

## 5
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
78 | setting out for door and window frame installation | door frame | door and window frame installation | routine | tape measure | blank | door/window
79 | setting out for door and window frame installation | window frame | door and window frame installation | routine | tape measure | blank | door/window
80 | dimension check for door and window frame installation | window frame | door and window frame installation | routine | tape measure | blank | door/window

## 6
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
100 | visual inspection for door frame fixing | door frame | fix door frame | 0.2 | N/A | blank | door/window
101 | visual inspection for door panel fixing | door panel | fixing door panel | 0.2 | N/A | qc inspector (factory) | door/window
104 | review sample for installation of hinges | hinge | installation?of?hinges | 0.2 | N/A | qc inspector (factory) | door/window
105 | visual inspection for installation of hinges | hinge | installation?of?hinges | 0.2 | N/A | qc inspector (factory) | door/window
108 | visual inspection for installation?of?overhead door closer | overhead door closer | installation?of?overhead door closer | 0.2 | N/A | blank | door/window
171 | review sample for window installation | aluminium window | window installation (glazing had fixed on the window) | 0.2 | N/A | blank | door/window
172 | visual inspection for window installation | aluminium window | window installation (glazing had fixed on the window) | 0.2 | N/A | blank | door/window

## 7
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
96 | setting out for door installation | door | setting out, establish floor level, and alignment | 0.2 | tape measure | blank | door/window
97 | establish floor level | floor | setting out, establish floor level, and alignment | 0.2 | tape measure | blank | door/window
103 | gap alignment check for door panel fixing | door panel | fixing door panel | 0.2 | tape measure | qc inspector (factory) | door/window
106 | verify compliance for installation of hinges | hinge | installation?of?hinges | 0.2 | tape measure | qc inspector (factory) | door/window
107 | review sample for installation?of?overhead door closer | overhead door closer | installation?of?overhead door closer | 0.2 | tape measure | blank | door/window
109 | verify compliance for installation?of?overhead door closer | overhead door closer | installation?of?overhead door closer | 0.2 | tape measure | blank | door/window
169 | check setting out for window installation | aluminium window | setting out, level, and alignment | 0.2 | tape measure | blank | door/window
173 | verify compliance for window installation | aluminium window | window installation (glazing had fixed on the window) | 0.2 | tape measure | blank | door/window

## 8
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
98 | establish floor level | floor | setting out, establish floor level, and alignment | 0.2 | level | blank | door/window
102 | proper installation check for door panel fixing | door panel | fixing door panel | 0.2 | level | qc inspector (factory) | door/window
170 | check level for window installation | aluminium window | setting out, level, and alignment | 0.2 | level | blank | door/window

## 9
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
99 | establish floor level | floor | setting out, establish floor level, and alignment | 0.2 | square | blank | door/window

## 10
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
110 | water spray test for door/window | timber door | door/window | blank | water spray system | blank | door/window
111 | water spray test for door/window | non-frp timber door | door/window | blank | water spray system | blank | door/window
112 | water spray test for door/window | frp timber door | door/window | blank | water spray system | blank | door/window
113 | water spray test for door/window | hardwood solid core flush doors | door/window | blank | water spray system | blank | door/window
114 | water spray test for door/window | aluminium window | door/window | blank | water spray system | blank | door/window

## 11
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
115 | electrical continuity test for door/window | timber door | door/window | blank | multimeter | blank | door/window
116 | electrical continuity test for door/window | non-frp timber door | door/window | blank | multimeter | blank | door/window
117 | electrical continuity test for door/window | frp timber door | door/window | blank | multimeter | blank | door/window
118 | electrical continuity test for door/window | hardwood solid core flush doors | door/window | blank | multimeter | blank | door/window
119 | electrical continuity test for door/window | aluminium window | door/window | blank | multimeter | blank | door/window

## 12
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
174 | check proper installation for earthing point setting during window installation | aluminium window | earthing point setting | 0.1 | multi-function tester | blank | door/window