## 1
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
322 | visual inspection for installation of mep trunking at ceiling (at common area) | ceiling panel | installation of mep trunking at ceiling (at common area) | routine | N/A | blank | electrical & mechanical
323 | visual inspection for installation of mep trunking at ceiling (at common area) | mep system | installation of mep trunking at ceiling (at common area) | routine | N/A | blank | electrical & mechanical
324 | visual inspection for installation of mep trunking at ceiling (at common area) | cable trunking | installation of mep trunking at ceiling (at common area) | routine | N/A | blank | electrical & mechanical
373 | visual inspection for the installation of sprinkler pipes (at hostel room) | sprinkler pipe | installation of sprinkler pipes (at hostel room) | routine | N/A | blank | electrical & mechanical
463 | visual inspection for installation of lighting | lighting fittings | installation of lighting / mep final fix | routine | N/A | blank | electrical & mechanical
464 | visual inspection for installation of lighting | lightings | installation of lighting / mep final fix | routine | N/A | blank | electrical & mechanical
465 | visual inspection for installation of lighting | battery lighting fittings | installation of lighting / mep final fix | routine | N/A | blank | electrical & mechanical
466 | visual inspection for mep final fix | mep system | installation of lighting / mep final fix | routine | N/A | blank | electrical & mechanical

## 2
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
405 | visual inspection for pipework execution | copper pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
406 | visual inspection for pipework execution | epoxy coated cast iron pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
407 | visual inspection for pipework execution | epoxy pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
408 | visual inspection for pipework execution | upvc pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
409 | visual inspection for pipework execution | galvanized steel pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
410 | surface check for pipework execution | copper pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
411 | surface check for pipework execution | epoxy coated cast iron pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
412 | surface check for pipework execution | epoxy pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
413 | surface check for pipework execution | upvc pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
414 | surface check for pipework execution | galvanized steel pipes | pipework execution | 0.2 | N/A | blank | electrical & mechanical
416 | visual inspection for painting and labelling for mep | mep system | painting and labelling | 0.2 | N/A | blank | electrical & mechanical
417 | surface check for painting and labelling for mep | mep system | painting and labelling | 0.2 | N/A | blank | electrical & mechanical

## 3
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
374 | sample for sprinkler heads | sprinkler heads | sprinkler heads | each batch | N/A | blank | electrical & mechanical
376 | visual inspection for sprinkler heads | sprinkler heads | sprinkler heads | each batch | N/A | blank | electrical & mechanical
380 | check temperatrure rating for sprinkler heads | sprinkler heads | sprinkler heads | each batch | N/A | blank | electrical & mechanical
381 | sample for fire detector | fire detector | fire detector | each batch | N/A | blank | electrical & mechanical
384 | each fire alarm bell shall be painted in red colour and clearly marked with the words "fire alarm"in both english and chinese in white colour.the height of all the english and chinese wordings shall not be less than 10mm and 15mm respectively. | fire alarm bells | fire alarm bells | each batch | N/A | blank | electrical & mechanical
393 | visual inspection for conduit system | conduit | conduit system | each batch | N/A | blank | electrical & mechanical
394 | visual inspection for conduit system | conduits and accessories | conduit system | each batch | N/A | blank | electrical & mechanical
395 | visual inspection for conduit system | flexible conduit belongs-to mep system | conduit system | each batch | N/A | blank | electrical & mechanical
396 | visual inspection for conduit system | upvc conduits and fittings | conduit system | each batch | N/A | blank | electrical & mechanical
397 | visual inspection for conduit system | flexible conduit | conduit system | each batch | N/A | blank | electrical & mechanical
398 | visual inspection for conduit system | mep conduit | conduit system | each batch | N/A | blank | electrical & mechanical
399 | surface check for conduit system | conduit | conduit system | each batch | N/A | blank | electrical & mechanical
400 | surface check for conduit system | conduits and accessories | conduit system | each batch | N/A | blank | electrical & mechanical
401 | surface check for conduit system | flexible conduit belongs-to mep system | conduit system | each batch | N/A | blank | electrical & mechanical
402 | surface check for conduit system | upvc conduits and fittings | conduit system | each batch | N/A | blank | electrical & mechanical
403 | surface check for conduit system | flexible conduit | conduit system | each batch | N/A | blank | electrical & mechanical
404 | surface check for conduit system | mep conduit | conduit system | each batch | N/A | blank | electrical & mechanical
415 | chinese and english language check for labelling for mep | mep system | labelling | each batch | N/A | blank | electrical & mechanical

## 4
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
325 | dimension check for cable tray execution | cable tray | cable tray | each batch | tape measure | blank | electrical & mechanical
328 | dimension check for cable trunking | cable trunking | cable trunking | each batch | tape measure | blank | electrical & mechanical
331 | dimension check for conduit system | conduit | conduit system | each batch | tape measure | blank | electrical & mechanical
334 | dimension check for conduit system | conduits and accessories | conduit system | each batch | tape measure | blank | electrical & mechanical
337 | dimension check for conduit system | flexible conduit belongs-to mep system | conduit system | each batch | tape measure | blank | electrical & mechanical
340 | dimension check for conduit system | upvc conduits and fittings | conduit system | each batch | tape measure | blank | electrical & mechanical
343 | dimension check for conduit system | upvc conduits | conduit system | each batch | tape measure | blank | electrical & mechanical
346 | dimension check for conduit system | flexible conduit | conduit system | each batch | tape measure | blank | electrical & mechanical
349 | dimension check for conduit system | mep conduit | conduit system | each batch | tape measure | blank | electrical & mechanical
352 | dimension check for conduit system | junction box | conduit / junction box / cable tray execution | each batch | tape measure | blank | electrical & mechanical
355 | dimension check for cable wiring | armoured wiring | cable wiring | each batch | tape measure | blank | electrical & mechanical
358 | dimension check for cable wiring | swa copper cable | cable wiring | each batch | tape measure | blank | electrical & mechanical
361 | dimension check for cable wiring | non-armoured cable | cable wiring | each batch | tape measure | blank | electrical & mechanical
364 | dimension check for cable wiring | pvc/ pvc cable | cable wiring | each batch | tape measure | blank | electrical & mechanical
367 | dimension check for cable wiring | pvc/swa/pvc copper cable | cable wiring | each batch | tape measure | blank | electrical & mechanical
370 | dimension check for cable wiring | pvc cables | cable wiring | each batch | tape measure | blank | electrical & mechanical
379 | vertical distance less than 800mm for sprinkler heads | sprinkler heads | sprinkler heads | each batch | tape measure | blank | electrical & mechanical
418 | dimension check for ductwork and fittings | ductwork and fittings | ductwork and fittings | each batch | tape measure | blank | electrical & mechanical
421 | dimension check for pipework and fittings | pipe fittings | pipework and fittings | each batch | tape measure | blank | electrical & mechanical
424 | dimension check for pipework and fittings | copper pipes | pipework and fittings | each batch | tape measure | blank | electrical & mechanical
427 | dimension check for pipework and fittings | epoxy coated cast iron pipes | pipework and fittings | each batch | tape measure | blank | electrical & mechanical
430 | dimension check for pipework and fittings | epoxy pipes | pipework and fittings | each batch | tape measure | blank | electrical & mechanical
433 | dimension check for pipework and fittings | upvc pipes | pipework and fittings | each batch | tape measure | blank | electrical & mechanical
436 | dimension check for pipework and fittings | galvanized steel pipes | pipework and fittings | each batch | tape measure | blank | electrical & mechanical
439 | dimension check for window type ac installation | ventilation fan | window type ac installation | each batch | tape measure | blank | electrical & mechanical
442 | dimension check for window type ac installation | carbon filter | window type ac installation | each batch | tape measure | blank | electrical & mechanical
445 | dimension check for window type ac installation | window type ac | window type ac installation | each batch | tape measure | blank | electrical & mechanical
448 | dimension check for window type ac installation | air filters | window type ac installation | each batch | tape measure | blank | electrical & mechanical
451 | dimension check for window type ac installation | activated carbon filter | window type ac installation | each batch | tape measure | blank | electrical & mechanical
454 | dimension check for window type ac installation | rubber vibration isolators | window type ac installation | each batch | tape measure | blank | electrical & mechanical
457 | dimension check for window type ac installation | spring vibration isolators | window type ac installation | each batch | tape measure | blank | electrical & mechanical
460 | dimension check for window type ac installation | air grilles/diffuser | window type ac installation | each batch | tape measure | blank | electrical & mechanical

## 5
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
326 | quantity check for cable tray execution | cable tray | cable tray | each batch | inventory checklist | blank | electrical & mechanical
329 | quantity check for cable trunking | cable trunking | cable trunking | each batch | inventory checklist | blank | electrical & mechanical
332 | quantity check for conduit system | conduit | conduit system | each batch | inventory checklist | blank | electrical & mechanical
335 | quantity check for conduit system | conduits and accessories | conduit system | each batch | inventory checklist | blank | electrical & mechanical
338 | quantity check for conduit system | flexible conduit belongs-to mep system | conduit system | each batch | inventory checklist | blank | electrical & mechanical
341 | quantity check for conduit system | upvc conduits and fittings | conduit system | each batch | inventory checklist | blank | electrical & mechanical
344 | quantity check for conduit system | upvc conduits | conduit system | each batch | inventory checklist | blank | electrical & mechanical
347 | quantity check for conduit system | flexible conduit | conduit system | each batch | inventory checklist | blank | electrical & mechanical
350 | quantity check for conduit system | mep conduit | conduit system | each batch | inventory checklist | blank | electrical & mechanical
353 | quantity check for conduit system | junction box | conduit / junction box / cable tray execution | each batch | inventory checklist | blank | electrical & mechanical
356 | quantity check for cable wiring | armoured wiring | cable wiring | each batch | inventory checklist | blank | electrical & mechanical
359 | quantity check for cable wiring | swa copper cable | cable wiring | each batch | inventory checklist | blank | electrical & mechanical
362 | quantity check for cable wiring | non-armoured cable | cable wiring | each batch | inventory checklist | blank | electrical & mechanical
365 | quantity check for cable wiring | pvc/ pvc cable | cable wiring | each batch | inventory checklist | blank | electrical & mechanical
368 | quantity check for cable wiring | pvc/swa/pvc copper cable | cable wiring | each batch | inventory checklist | blank | electrical & mechanical
371 | quantity check for cable wiring | pvc cables | cable wiring | each batch | inventory checklist | blank | electrical & mechanical
419 | quantity check for ductwork and fittings | ductwork and fittings | ductwork and fittings | each batch | inventory checklist | blank | electrical & mechanical
422 | quantity check for pipework and fittings | pipe fittings | pipework and fittings | each batch | inventory checklist | blank | electrical & mechanical
425 | quantity check for pipework and fittings | copper pipes | pipework and fittings | each batch | inventory checklist | blank | electrical & mechanical
428 | quantity check for pipework and fittings | epoxy coated cast iron pipes | pipework and fittings | each batch | inventory checklist | blank | electrical & mechanical
431 | quantity check for pipework and fittings | epoxy pipes | pipework and fittings | each batch | inventory checklist | blank | electrical & mechanical
434 | quantity check for pipework and fittings | upvc pipes | pipework and fittings | each batch | inventory checklist | blank | electrical & mechanical
437 | quantity check for pipework and fittings | galvanized steel pipes | pipework and fittings | each batch | inventory checklist | blank | electrical & mechanical
440 | quantity check for window type ac installation | ventilation fan | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
443 | quantity check for window type ac installation | carbon filter | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
446 | quantity check for window type ac installation | window type ac | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
449 | quantity check for window type ac installation | air filters | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
452 | quantity check for window type ac installation | activated carbon filter | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
455 | quantity check for window type ac installation | rubber vibration isolators | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
458 | quantity check for window type ac installation | spring vibration isolators | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical
461 | quantity check for window type ac installation | air grilles/diffuser | window type ac installation | each batch | inventory checklist | blank | electrical & mechanical

## 6
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
327 | material certificate check for cable tray execution | cable tray | cable tray | each batch | mill certificate | blank | electrical & mechanical
330 | material certificate check for cable trunking | cable trunking | cable trunking | each batch | mill certificate | blank | electrical & mechanical
333 | material certificate check for conduit system | conduit | conduit system | each batch | mill certificate | blank | electrical & mechanical
336 | material certificate check for conduit system | conduits and accessories | conduit system | each batch | mill certificate | blank | electrical & mechanical
339 | material certificate check for conduit system | flexible conduit belongs-to mep system | conduit system | each batch | mill certificate | blank | electrical & mechanical
342 | material certificate check for conduit system | upvc conduits and fittings | conduit system | each batch | mill certificate | blank | electrical & mechanical
345 | material certificate check for conduit system | upvc conduits | conduit system | each batch | mill certificate | blank | electrical & mechanical
348 | material certificate check for conduit system | flexible conduit | conduit system | each batch | mill certificate | blank | electrical & mechanical
351 | material certificate check for conduit system | mep conduit | conduit system | each batch | mill certificate | blank | electrical & mechanical
354 | material certificate check for conduit system | junction box | conduit / junction box / cable tray execution | each batch | mill certificate | blank | electrical & mechanical
357 | material certificate check for cable wiring | armoured wiring | cable wiring | each batch | mill certificate | blank | electrical & mechanical
360 | material certificate check for cable wiring | swa copper cable | cable wiring | each batch | mill certificate | blank | electrical & mechanical
363 | material certificate check for cable wiring | non-armoured cable | cable wiring | each batch | mill certificate | blank | electrical & mechanical
366 | material certificate check for cable wiring | pvc/ pvc cable | cable wiring | each batch | mill certificate | blank | electrical & mechanical
369 | material certificate check for cable wiring | pvc/swa/pvc copper cable | cable wiring | each batch | mill certificate | blank | electrical & mechanical
372 | material certificate check for cable wiring | pvc cables | cable wiring | each batch | mill certificate | blank | electrical & mechanical
420 | material certificate check for ductwork and fittings | ductwork and fittings | ductwork and fittings | each batch | mill certificate | blank | electrical & mechanical
423 | material certificate for pipework and fittings | pipe fittings | pipework and fittings | each batch | mill certificate | blank | electrical & mechanical
426 | material certificate for pipework and fittings | copper pipes | pipework and fittings | each batch | mill certificate | blank | electrical & mechanical
429 | material certificate for pipework and fittings | epoxy coated cast iron pipes | pipework and fittings | each batch | mill certificate | blank | electrical & mechanical
432 | material certificate for pipework and fittings | epoxy pipes | pipework and fittings | each batch | mill certificate | blank | electrical & mechanical
435 | material certificate for pipework and fittings | upvc pipes | pipework and fittings | each batch | mill certificate | blank | electrical & mechanical
438 | material certificate for pipework and fittings | galvanized steel pipes | pipework and fittings | each batch | mill certificate | blank | electrical & mechanical
441 | material certificate for window type ac installation | ventilation fan | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
444 | material certificate for window type ac installation | carbon filter | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
447 | material certificate for window type ac installation | window type ac | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
450 | material certificate for window type ac installation | air filters | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
453 | material certificate for window type ac installation | activated carbon filter | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
456 | material certificate for window type ac installation | rubber vibration isolators | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
459 | material certificate for window type ac installation | spring vibration isolators | window type ac installation | each batch | mill certificate | blank | electrical & mechanical
462 | material certificate for window type ac installation | air grilles/diffuser | window type ac installation | each batch | mill certificate | blank | electrical & mechanical

## 7
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
385 | all pipes shall be new and shall be thoroughly cleaned | copper pipes | pipes | each batch | brush | blank | electrical & mechanical
386 | all pipes shall be new and shall be thoroughly cleaned | epoxy coated cast iron pipes | pipes | each batch | brush | blank | electrical & mechanical
387 | all pipes shall be new and shall be thoroughly cleaned | epoxy pipes | pipes | each batch | brush | blank | electrical & mechanical
388 | all pipes shall be new and shall be thoroughly cleaned | upvc pipes | pipes | each batch | brush | blank | electrical & mechanical
389 | all pipes shall be new and shall be thoroughly cleaned | galvanized steel pipes | pipes | each batch | brush | blank | electrical & mechanical
390 | sample for pipe fittings | pipe fittings | pipe fittings | each batch | brush | blank | electrical & mechanical

## 8
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
383 | check properties for fire detector | fire detector | fire detector | each batch | functional test tool | blank | electrical & mechanical
392 | check properties for pipe fittings | pipe fittings | pipe fittings | each batch | functional test tool | blank | electrical & mechanical

## 9
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
377 | measure dimension for sprinkler heads | sprinkler heads | sprinkler heads | each batch | caliper | blank | electrical & mechanical
378 | 3mm thickness check for sprinkler heads | sprinkler heads | sprinkler heads | each batch | caliper | blank | electrical & mechanical

## 10
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
375 | brand name check for sprinkler heads | sprinkler heads | sprinkler heads | each batch | bill of materials | blank | electrical & mechanical
382 | brand name check for fire detector | fire detector | fire detector | each batch | bill of materials | blank | electrical & mechanical
391 | brand name check for pipe fittings | pipe fittings | pipe fittings | each batch | bill of materials | blank | electrical & mechanical