## 1
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
314 | brand name check for emulsion paint delivered to site | emulsion paint | emulsion paint delivered to site | each batch | bill of materials | blank | print

## 2
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
315 | visual inspection for emulsion paint delivered to site | emulsion paint | emulsion paint delivered to site | each batch | N/A | blank | print

## 3
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
311 | visual inspection for second layer painting | wall panel | second layer painting | routine | N/A | blank | print
312 | visual inspection for second layer painting | ceiling panel | second layer painting | routine | N/A | blank | print

## 4
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
307 | visual inspection for gypsum plaster and sanding (wall and ceiling) | wall panel | gypsum plaster and sanding (wall and ceiling) | routine | N/A | blank | print
308 | visual inspection for gypsum plaster and sanding (wall and ceiling) | ceiling panel | gypsum plaster and sanding (wall and ceiling) | routine | N/A | blank | print

## 5
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
309 | visual inspection for first layer painting (hostel room and corridor) | wall panel | first layer painting (hostel room and corridor) | routine | N/A | blank | print
310 | visual inspection for first layer painting (hostel room and corridor) | ceiling panel | first layer painting (hostel room and corridor) | routine | N/A | blank | print

## 6
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
313 | visual inspection for top coat paint (ceiling) | ceiling panel | top coat paint (ceiling) | routine | N/A | blank | print

## 7
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
316 | visual inspection for substrades checking for skim coat plastering | wall substrade | substrades checking for skim coat plastering | 0.2 | N/A | blank | print
317 | verify compliance for substrades checking for skim coat plastering | wall substrade | substrades checking for skim coat plastering | 0.2 | N/A | blank | print

## 8
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
318 | visual inspection for applying prime (before painting emulsion paint) | wall panel | apply prime (before painting emulsion paint) | 0.2 | N/A | blank | print
319 | verify compliance for applying prime (before painting emulsion paint) | wall panel | apply prime (before painting emulsion paint) | 0.2 | N/A | blank | print

## 9
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
320 | visual inspection for apply emulsion painting (2 layers) | wall panel | apply emulsion painting (2 layers) | 0.2 | N/A | blank | print

## 10
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
321 | verify compliance for apply emulsion painting (2 layers) | emulsion paint | apply emulsion painting (2 layers) | 0.2 | N/A | blank | print