## 1
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
473 | sample for seal, seal accessories | structual sealant | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
474 | brand name check for seal, seal accessories | structual sealant | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | bill of materials | blank | testing and commissioning
475 | visual inspection for seal, seal accessories | structual sealant | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
476 | colour check for seal, seal accessories | structual sealant | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
477 | structual sealant 25% for seal, seal accessories | structual sealant | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | tensile testing machine | blank | testing and commissioning
478 | movement capability check for seal, seal accessories | structual sealant | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | technical specification | blank | testing and commissioning
479 | sample for seal, seal accessories | weather sealants | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
480 | brand name check for seal, seal accessories | weather sealants | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | bill of materials | blank | testing and commissioning
481 | visual inspection for seal, seal accessories | weather sealants | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
482 | colour check for seal, seal accessories | weather sealants | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
483 | movement capability check for seal, seal accessories | weather sealants | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | tensile testing machine | blank | testing and commissioning
484 | weather sealant 50% check for seal, seal accessories | weather sealants | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | technical specification | blank | testing and commissioning
485 | sample for seal, seal accessories | backer rods | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
486 | brand name check for seal, seal accessories | backer rods | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | bill of materials | blank | testing and commissioning
487 | visual inspection for seal, seal accessories | backer rods | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
488 | colour check for seal, seal accessories | backer rods | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
489 | movement capability check for seal, seal accessories | backer rods | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | tensile testing machine | blank | testing and commissioning
490 | sample for seal, seal accessories | tapes | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | technical specification | blank | testing and commissioning
491 | brand name check for seal, seal accessories | tapes | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
492 | visual inspection for seal, seal accessories | tapes | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | bill of materials | blank | testing and commissioning
493 | colour check for seal, seal accessories | tapes | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
494 | colour check for seal, seal accessories | gasket | seal, seal accessories (structual sealant, weather sealants, backer rods, tapes, etc) | each batch | N/A | blank | testing and commissioning
495 | sample for gasket | gasket | gasket | each batch | N/A | blank | testing and commissioning
496 | brand name check for gasket | gasket | gasket | each batch | bill of materials | blank | testing and commissioning
497 | gasket profiles not less than 0.7n/mm | gasket | gasket | each batch | tensile testing machine | blank | testing and commissioning
498 | minimum 3mm thickness, with maximun 5% thickness tolerance for setting blocks | setting blocks | setting blocks | each batch | digital vernier scale | blank | testing and commissioning
499 | aluminium for external cladding not less than 3mm thickness | aluminium for external cladding | aluminium | each batch | digital vernier scale | blank | testing and commissioning
500 | sample for fixing and anchorages | fixing and anchorages | fixing and anchorages | each batch | N/A | blank | testing and commissioning
501 | brand name check for fixing and anchorages | fixing and anchorages | fixing and anchorages | each batch | bill of materials | blank | testing and commissioning
502 | visual check type and size for fixing and anchorages | fixing and anchorages | fixing and anchorages | each batch | N/A | blank | testing and commissioning
503 | minimum 3mm thickness check for backpan | backpan | backpan | each batch | digital vernier scale | blank | testing and commissioning
504 | sample for insulation | rockwool acoustic insulation | insulation | each batch | N/A | blank | testing and commissioning
505 | brand name check for insulation | rockwool acoustic insulation | insulation | each batch | bill of materials | blank | testing and commissioning
506 | visual inspection for insulation | rockwool acoustic insulation | insulation | each batch | N/A | blank | testing and commissioning
507 | sample for insulation | acoustic insulation | insulation | each batch | N/A | blank | testing and commissioning
508 | brand name check for insulation | acoustic insulation | insulation | each batch | bill of materials | blank | testing and commissioning
509 | visual inspection for insulation | acoustic insulation | insulation | each batch | N/A | blank | testing and commissioning
510 | sample for insulation | mineral wool insulation | insulation | each batch | N/A | blank | testing and commissioning
511 | brand name check for insulation | mineral wool insulation | insulation | each batch | bill of materials | blank | testing and commissioning
512 | visual inspection for insulation | mineral wool insulation | insulation | each batch | N/A | blank | testing and commissioning
513 | minimium 0.6mm thicknes check for flashings | flashings | flashings | each batch | digital vernier scale | blank | testing and commissioning
517 | brand name check for vinyl floor installation | pvc sheet vinyl/vinyl floor | pvc sheet vinyl | each batch | N/A | blank | testing and commissioning
518 | approval sample for vinyl floor installation | pvc sheet vinyl/vinyl floor | pvc sheet vinyl | each batch | N/A | blank | testing and commissioning
519 | visual surface check for vinyl floor installation | pvc sheet vinyl/vinyl floor | pvc sheet vinyl | each batch | N/A | blank | testing and commissioning
520 | dimension and thickness check for vinyl floor installation | pvc sheet vinyl/vinyl floor | pvc sheet vinyl | each batch | tape measure | blank | testing and commissioning
530 | brand name check for laminate | plastic laminate | plastic laminate | each batch | bill of materials | blank | testing and commissioning
531 | approval sample for laminate | plastic laminate | plastic laminate | each batch | N/A | blank | testing and commissioning
532 | visual surface check for laminate | plastic laminate | plastic laminate | each batch | N/A | blank | testing and commissioning
533 | dimension check for laminate | plastic laminate | plastic laminate | each batch | tape measure | blank | testing and commissioning
534 | thickness check for laminate | plastic laminate | plastic laminate | each batch | caliper | blank | testing and commissioning
535 | brand name check for wood | wood (veneer type and solid stock type) | wood (veneer type and solid stock type) | each batch | bill of materials | blank | testing and commissioning
536 | approval sample for wood | wood (veneer type and solid stock type) | wood (veneer type and solid stock type) | each batch | N/A | blank | testing and commissioning
537 | wood preservative check for wood | wood (veneer type and solid stock type) | wood (veneer type and solid stock type) | each batch | N/A | blank | testing and commissioning
538 | dimension check for wood | wood (veneer type and solid stock type) | wood (veneer type and solid stock type) | each batch | tape measure | blank | testing and commissioning
539 | thickness check for wood | wood (veneer type and solid stock type) | wood (veneer type and solid stock type) | each batch | caliper | blank | testing and commissioning
540 | brand name check for shelf supports | shelf supports | shelf supports | each batch | bill of materials | blank | testing and commissioning
541 | approval sample for shelf supports | shelf supports | shelf supports | each batch | N/A | blank | testing and commissioning
542 | visual inspection for shelf supports | shelf supports | shelf supports | each batch | N/A | blank | testing and commissioning

## 2
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
564 | water-tightness test for window installation | window | water-tightness tests | 1 | water spray system | blank | testing and commissioning
571 | 3d scanning with dimension check | MiC module | MiC geometry | 1 | laser equipment | blank | testing and commissioning
572 | final overall check for waterproofing | MiC module | waterproofing | 1 | water spray system | blank | testing and commissioning
573 | final overall check for steel and metal work | MiC module | steel and metal work | 1 | welding inspection mirror | blank | testing and commissioning
574 | final overall check for carpentry and joinery | MiC module | carpentry and joinery | 1 | tape measure | blank | testing and commissioning
575 | final overall check for roofing | MiC module | roofing | 1 | hydrostatic testing equipment | blank | testing and commissioning
576 | final overall check for finishes | MiC module | finishes | 1 | N/A | blank | testing and commissioning
577 | final overall check for sanitary fitting | MiC module | sanitary fitting | 1 | N/A | blank | testing and commissioning
578 | final overall check for aluminium windows | MiC module | aluminium windows | 1 | sealant test tool | blank | testing and commissioning
579 | final overall check for ironmongery | MiC module | ironmongery | 1 | torque wrench | blank | testing and commissioning
580 | final overall check for expansion joints | MiC module | expansion joints | 1 | N/A | blank | testing and commissioning
581 | final overall check for drywall partitions | MiC module | drywall partitions | 1 | N/A | blank | testing and commissioning
582 | final overall check for acoustic requirment | MiC module | acoustic requirment | 1 | sound level meter | blank | testing and commissioning
583 | final overall check for signage and graphes | MiC module | signage and graphes | 1 | N/A | blank | testing and commissioning
584 | final overall check for loose and fix furniture | furniture | loose and fix furniture | 1 | N/A | blank | testing and commissioning
585 | final overall check for fireproofing | MiC module | fireproofing | 1 | flame test tool | blank | testing and commissioning
586 | final overall check for fa?ade | MiC module | fa?ade | 1 | facade inspection mirror | blank | testing and commissioning
587 | final overall check for structure | MiC module | structure | 1 | crack width gauge | blank | testing and commissioning
588 | final overall check for building services | MiC module | building services | 1 | multi-function tester | blank | testing and commissioning
591 | protection and package check | MiC module | external protection on mic unit | 1 | N/A | blank | testing and commissioning
592 | protection and package check | MiC module | internal protection on interior element (i.e. finishes, window, door, fix furniture, building service, etc) | 1 | N/A | blank | testing and commissioning
593 | protection and package check | MiC module | package on loose furniture | 1 | N/A | blank | testing and commissioning
594 | protection and package check | MiC module | package on electric appliance | 1 | N/A | blank | testing and commissioning
595 | protection and package check | MiC module | package on material(to be post installation on site) | 1 | N/A | blank | testing and commissioning

## 3
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
514 | installed as approved working drawing and comply with performance requirements, codes, standards/requirement of the relevant | fa?ade system | installation of fa?ade system | 0.2 | N/A | blank | testing and commissioning
515 | operation assurance for hardware installation | hardware | hardware installation | 0.2 | N/A | blank | testing and commissioning
516 | plumb, level and aligned with required torlerance check for sub-framing | sub frame | sub-framing | 0.2 | level | blank | testing and commissioning
521 | check setting out compliance for vinyl floor installation | pvc sheet vinyl/vinyl floor | setting out befor prior work commencement | 0.2 | tape measure | blank | testing and commissioning
522 | visual inspection for vinyl floor installation | pvc sheet vinyl/vinyl floor | installation of vinyl floor | 0.2 | N/A | blank | testing and commissioning
543 | check setting out(dimension and shop drawing detail) for furniture | furniture | setting out | 0.2 | tape measure | blank | testing and commissioning
544 | visual inspection for component construction and installation of furniture | furniture | component construction and installation of furniture (i.e. hostel desk and wall hang shelf, hostel cabinet,hostel bed) | 0.2 | N/A | blank | testing and commissioning
545 | dimension and design requirement check for component construction and installation of furniture | furniture | component construction and installation of furniture (i.e. hostel desk and wall hang shelf, hostel cabinet,hostel bed) | 0.2 | tape measure | blank | testing and commissioning
546 | protected by polyurethane sheeting or other suitable protection | furniture | protection of work | 0.2 | N/A | blank | testing and commissioning
547 | removal any soiled spots from face of finish surface of furniture | furniture | cleaning | 0.2 | cleaning tool | blank | testing and commissioning
548 | review sample for installation?of?locksets | locksets | installation?of?locksets | 0.2 | N/A | blank | testing and commissioning
549 | visual inspection for installation?of?locksets | locksets | installation?of?locksets | 0.2 | N/A | blank | testing and commissioning
550 | verify compliance for installation?of?locksets | locksets | installation?of?locksets | 0.2 | N/A | blank | testing and commissioning
551 | review sample for installation?of?floor door stop | floor door stop | installation?of?floor door stop | 0.2 | N/A | blank | testing and commissioning
552 | visual inspection for installation?of?floor door stop | floor door stop | installation?of?floor door stop | 0.2 | N/A | blank | testing and commissioning
553 | verify compliance for installation?of?floor door stop | floor door stop | installation?of?floor door stop | 0.2 | N/A | blank | testing and commissioning

## 4
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
554 | visual inspection for grouting behind the frame back | window frame | grouting behind the frame back | 0.1 | N/A | blank | testing and commissioning
555 | verify compliance for grouting behind the frame back | window frame | grouting behind the frame back | 0.1 | N/A | blank | testing and commissioning
556 | visual inspection for sealant and gasket application at window | aluminium window | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
557 | visual inspection for sealant and gasket application at window | structual sealant | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
558 | visual inspection for sealant and gasket application at window | weather sealants | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
559 | visual inspection for sealant and gasket application at window | gasket | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
560 | surface check for sealant and gasket application at window | aluminium window | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
561 | surface check for sealant and gasket application at window | gasket | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
562 | surface check for sealant and gasket application at window | structual sealant | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning
563 | surface check for sealant and gasket application at window | weather sealants | sealant and gasket application | 0.1 | N/A | blank | testing and commissioning

## 5
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
467 | visual inspection for cladding panel installation/ top coat wall paint | promatect hboard | cladding panel installation/ top coat wall paint | routine | N/A | blank | testing and commissioning
468 | visual inspection for cladding panel installation/ top coat wall paint | knauf frp board | cladding panel installation/ top coat wall paint | routine | N/A | blank | testing and commissioning
469 | visual inspection for cladding panel installation/ top coat wall paint | gemtree frp board | cladding panel installation/ top coat wall paint | routine | N/A | blank | testing and commissioning
470 | visual inspection for cladding panel installation/ top coat wall paint | gypsum board | cladding panel installation/ top coat wall paint | routine | N/A | blank | testing and commissioning
471 | visual inspection for cladding panel installation/ top coat wall paint | cement board | cladding panel installation/ top coat wall paint | routine | N/A | blank | testing and commissioning
472 | visual inspection for cladding panel installation/ top coat wall paint | emulsion paint | cladding panel installation/ top coat wall paint | routine | N/A | blank | testing and commissioning
523 | visual inspection for cabinets/ wardrobe installation | sink cabinet | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
524 | visual inspection for cabinets/ wardrobe installation | toilet cabinet | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
525 | visual inspection for cabinets/ wardrobe installation | tv cabinet | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
526 | visual inspection for cabinets/ wardrobe installation | wall cabinet | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
527 | visual inspection for cabinets/ wardrobe installation | cabinets | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
528 | visual inspection for cabinets/ wardrobe installation | toilet-sink cabinet | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
529 | visual inspection for cabinets/ wardrobe installation | wardrobe | cabinets/ wardrobe installation | routine | N/A | blank | testing and commissioning
565 | visual inspection for general cleaning and floor protection | floor/vinyl floor | general cleaning and floor protection | routine | N/A | blank | testing and commissioning
566 | visual inspection for packing and protection of furniture | furniture | packing and protection of furniture | routine | N/A | blank | testing and commissioning
567 | mep final check (air conditioning, fire suppression, electrical) | mep system | mep final check (air conditioning, fire suppression, electrical) | routine | N/A | blank | testing and commissioning
568 | 3d dimension check during testing and commissioning | MiC module | 3d dimension check | routine | tape measure | blank | testing and commissioning
569 | paint touch-up | MiC module | paint touch-up | routine | paint | blank | testing and commissioning
570 | final qc inspection | MiC module | final qc inspection | routine | N/A | blank | testing and commissioning
589 | visual inspection for labling of MiC module | MiC module | labling of MiC module, packaging and protection mic module | routine | N/A | blank | testing and commissioning
590 | visual inspection for MiC module packaging and protection | MiC module | labling of MiC module, packaging and protection mic module | routine | N/A | blank | testing and commissioning