## 1
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
175 | visual inspection for ceiling stud installation at ceiling surface | shear stud | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
176 | visual inspection for ceiling stud installation at ceiling surface | noggins and braces for reinforced stud support | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
177 | visual inspection for ceiling stud installation at ceiling surface | ceiling panel | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
178 | visual inspection for ceiling stud installation at ceiling surface | steel ceiling beam | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
179 | visual inspection for ceiling stud installation at ceiling surface | track for stud installation | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
180 | visual inspection for ceiling stud installation at ceiling surface | channel | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
181 | visual inspection for ceiling stud installation at ceiling surface | runners | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
182 | visual inspection for ceiling stud installation at ceiling surface | metal skeleton | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
183 | visual inspection for rockwool in-fill at ceiling surface | mineral wool insulation | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
184 | visual inspection for rockwool in-fill at ceiling surface | rockwool | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
185 | visual inspection for fire board installation at ceiling surface | promatect hboard | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
186 | visual inspection for fire board installation at ceiling surface | gemtree board | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
187 | visual inspection for fire board installation at ceiling surface | gemtree frp board | ceiling stud, rockwool in-fill and fire board installation at ceiling surface | blank | N/A | authorized persons | wall
188 | visual inspection for wall stud installation | shear stud | fire board, wall stud installation | blank | N/A | authorized persons | wall
189 | visual inspection for wall stud installation | noggins and braces for reinforced stud support | fire board, wall stud installation | blank | N/A | authorized persons | wall
190 | visual inspection for wall stud installation | wall panel | fire board, wall stud installation | blank | N/A | authorized persons | wall
191 | visual inspection for wall stud installation | wall tiles | fire board, wall stud installation | blank | N/A | authorized persons | wall
192 | visual inspection for wall stud installation | track for stud installation | fire board, wall stud installation | blank | N/A | authorized persons | wall
193 | visual inspection for wall stud installation | channel | fire board, wall stud installation | blank | N/A | authorized persons | wall
194 | visual inspection for wall stud installation | runners | fire board, wall stud installation | blank | N/A | authorized persons | wall
195 | visual inspection for wall stud installation | wall system contains wall panel | fire board, wall stud installation | blank | N/A | authorized persons | wall
196 | visual inspection for wall stud installation | metal skeleton | fire board, wall stud installation | blank | N/A | authorized persons | wall
197 | visual inspection for fire board installation at wall | promatect hboard | fire board, wall stud installation | blank | N/A | authorized persons | wall
198 | visual inspection for fire board installation at wall | gemtree board | fire board, wall stud installation | blank | N/A | authorized persons | wall
199 | visual inspection for fire board installation at wall | gemtree frp board | fire board, wall stud installation | blank | N/A | authorized persons | wall
200 | visual inspection for rockwool in-fill at wall surface | mineral wool insulation | rockwool in-fill at wall surface | blank | N/A | authorized persons | wall
201 | visual inspection for rockwool in-fill at wall surface | rockwool | rockwool in-fill at wall surface | blank | N/A | authorized persons | wall

## 2
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
245 | check support fixtures for top and bottom track installation | track | top and bottom track installation | 0.2 | level | blank | wall
247 | check steel stud vertical and horizontal alignment for vertical stud installation frame core | stud | vertical stud installation frame core | 0.2 | level | blank | wall

## 3
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
241 | check setting out(location, area, thickness) for wall installation | wall panel | setting out(location, area, thickness) | 0.2 | tape measure | blank | wall
242 | check setting out(location, area, thickness) for wall installation | wall tiles | setting out(location, area, thickness) | 0.2 | tape measure | blank | wall
243 | dimension check for wall installation | wall panel | setting out(location, area, thickness) | 0.2 | tape measure | blank | wall
244 | dimension check for wall installation | wall tiles | setting out(location, area, thickness) | 0.2 | tape measure | blank | wall
246 | check support fixtures for top and bottom track installation | track | top and bottom track installation | 0.2 | tape measure | blank | wall
248 | check space and workmanship for vertical stud installation frame core | stud | vertical stud installation frame core | 0.2 | tape measure | blank | wall
259 | check the cutting and surface for installation of external wall sheeting | knauf frp board | installation of external wall sheeting | 0.2 | tape measure | blank | wall
260 | check the cutting and surface for installation of external wall sheeting | promatect hboard | installation of external wall sheeting | 0.2 | tape measure | blank | wall
261 | check the cutting and surface for installation of external wall sheeting | cement board | installation of external wall sheeting | 0.2 | tape measure | blank | wall
262 | check the cutting and surface for installation of external wall sheeting | gemtree frp board | installation of external wall sheeting | 0.2 | tape measure | blank | wall
263 | check the cutting and surface for installation of external wall sheeting | gypsum board | installation of external wall sheeting | 0.2 | tape measure | blank | wall
278 | verify compliance for rockwool installation at wall | rockwool | rockwool installation | 0.2 | tape measure | blank | wall
279 | verify compliance for rockwool installation at wall | mineral wool insulation | rockwool installation | 0.2 | tape measure | blank | wall
290 | check the cutting and surface for installation of internal wall sheeting | knauf frp board | installation of internal wall sheeting | 0.2 | tape measure | blank | wall
291 | check the cutting and surface for installation of internal wall sheeting | promatect hboard | installation of internal wall sheeting | 0.2 | tape measure | blank | wall
292 | check the cutting and surface for installation of internal wall sheeting | cement board | installation of internal wall sheeting | 0.2 | tape measure | blank | wall
293 | check the cutting and surface for installation of internal wall sheeting | gemtree frp board | installation of internal wall sheeting | 0.2 | tape measure | blank | wall
294 | check the cutting and surface for installation of internal wall sheeting | gypsum board | installation of internal wall sheeting | 0.2 | tape measure | blank | wall
306 | check tolerance for cutting opening width and height | provisional openings | provisional openings checking | 0.2 | tape measure | blank | wall

## 4
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
264 | visual check smooth for installation of external wall sheeting | knauf frp board | installation of external wall sheeting | 0.2 | N/A | blank | wall
265 | visual check smooth for installation of external wall sheeting | promatect hboard | installation of external wall sheeting | 0.2 | N/A | blank | wall
266 | visual check smooth for installation of external wall sheeting | cement board | installation of external wall sheeting | 0.2 | N/A | blank | wall
267 | visual check smooth for installation of external wall sheeting | gemtree frp board | installation of external wall sheeting | 0.2 | N/A | blank | wall
268 | visual check smooth for installation of external wall sheeting | gypsum board | installation of external wall sheeting | 0.2 | N/A | blank | wall
274 | review sample for rockwool installation at wall | rockwool | rockwool installation | 0.2 | N/A | blank | wall
275 | review sample for rockwool installation at wall | mineral wool insulation | rockwool installation | 0.2 | N/A | blank | wall
276 | visual check firmness and fullness for rockwool installation at wall | rockwool | rockwool installation | 0.2 | N/A | blank | wall
277 | visual check firmness and fullness for rockwool installation at wall | mineral wool insulation | rockwool installation | 0.2 | N/A | blank | wall
295 | visual check smooth for installation of internal wall sheeting | knauf frp board | installation of internal wall sheeting | 0.2 | N/A | blank | wall
296 | visual check smooth for installation of internal wall sheeting | promatect hboard | installation of internal wall sheeting | 0.2 | N/A | blank | wall
297 | visual check smooth for installation of internal wall sheeting | cement board | installation of internal wall sheeting | 0.2 | N/A | blank | wall
298 | visual check smooth for installation of internal wall sheeting | gemtree frp board | installation of internal wall sheeting | 0.2 | N/A | blank | wall
299 | visual check smooth for installation of internal wall sheeting | gypsum board | installation of internal wall sheeting | 0.2 | N/A | blank | wall
305 | visual check and verify compliance for installed drywall framing | drywall | installed drywall framing | 0.2 | N/A | blank | wall

## 5
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
269 | free from other contaminates for installation of external wall sheeting | knauf frp board | installation of external wall sheeting | 0.2 | brush | blank | wall
270 | free from other contaminates for installation of external wall sheeting | promatect hboard | installation of external wall sheeting | 0.2 | brush | blank | wall
271 | free from other contaminates for installation of external wall sheeting | cement board | installation of external wall sheeting | 0.2 | brush | blank | wall
272 | free from other contaminates for installation of external wall sheeting | gemtree frp board | installation of external wall sheeting | 0.2 | brush | blank | wall
273 | free from other contaminates for installation of external wall sheeting | gypsum board | installation of external wall sheeting | 0.2 | brush | blank | wall
300 | free from other contaminates for installation of internal wall sheeting | knauf frp board | installation of internal wall sheeting | 0.2 | brush | blank | wall
301 | free from other contaminates for installation of internal wall sheeting | promatect hboard | installation of internal wall sheeting | 0.2 | brush | blank | wall
302 | free from other contaminates for installation of internal wall sheeting | cement board | installation of internal wall sheeting | 0.2 | brush | blank | wall
303 | free from other contaminates for installation of internal wall sheeting | gemtree frp board | installation of internal wall sheeting | 0.2 | brush | blank | wall
304 | free from other contaminates for installation of internal wall sheeting | gypsum board | installation of internal wall sheeting | 0.2 | brush | blank | wall

## 6
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
249 | thickness check for installation of external wall sheeting | knauf frp board | installation of external wall sheeting | 0.2 | caliper | blank | wall
250 | thickness check for installation of external wall sheeting | promatect hboard | installation of external wall sheeting | 0.2 | caliper | blank | wall
251 | thickness check for installation of external wall sheeting | cement board | installation of external wall sheeting | 0.2 | caliper | blank | wall
252 | thickness check for installation of external wall sheeting | gemtree frp board | installation of external wall sheeting | 0.2 | caliper | blank | wall
253 | thickness check for installation of external wall sheeting | gypsum board | installation of external wall sheeting | 0.2 | caliper | blank | wall
280 | thickness check for installation of internal wall sheeting | knauf frp board | installation of internal wall sheeting | 0.2 | caliper | blank | wall
281 | thickness check for installation of internal wall sheeting | promatect hboard | installation of internal wall sheeting | 0.2 | caliper | blank | wall
282 | thickness check for installation of internal wall sheeting | cement board | installation of internal wall sheeting | 0.2 | caliper | blank | wall
283 | thickness check for installation of internal wall sheeting | gemtree frp board | installation of internal wall sheeting | 0.2 | caliper | blank | wall
284 | thickness check for installation of internal wall sheeting | gypsum board | installation of internal wall sheeting | 0.2 | caliper | blank | wall

## 7
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
254 | check the fixing at joint and at screwheads for installation of external wall sheeting | knauf frp board | installation of external wall sheeting | 0.2 | torque wrench | blank | wall
255 | check the fixing at joint and at screwheads for installation of external wall sheeting | promatect hboard | installation of external wall sheeting | 0.2 | torque wrench | blank | wall
256 | check the fixing at joint and at screwheads for installation of external wall sheeting | cement board | installation of external wall sheeting | 0.2 | torque wrench | blank | wall
257 | check the fixing at joint and at screwheads for installation of external wall sheeting | gemtree frp board | installation of external wall sheeting | 0.2 | torque wrench | blank | wall
258 | check the fixing at joint and at screwheads for installation of external wall sheeting | gypsum board | installation of external wall sheeting | 0.2 | torque wrench | blank | wall
285 | check the fixing at joint and at screwheads for installation of internal wall sheeting | knauf frp board | installation of internal wall sheeting | 0.2 | torque wrench | blank | wall
286 | check the fixing at joint and at screwheads for installation of internal wall sheeting | promatect hboard | installation of internal wall sheeting | 0.2 | torque wrench | blank | wall
287 | check the fixing at joint and at screwheads for installation of internal wall sheeting | cement board | installation of internal wall sheeting | 0.2 | torque wrench | blank | wall
288 | check the fixing at joint and at screwheads for installation of internal wall sheeting | gemtree frp board | installation of internal wall sheeting | 0.2 | torque wrench | blank | wall
289 | check the fixing at joint and at screwheads for installation of internal wall sheeting | gypsum board | installation of internal wall sheeting | 0.2 | torque wrench | blank | wall

## 8
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
215 | visual inspection for metal skeleton | stud | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | N/A | blank | wall
216 | visual inspection for metal skeleton | runners | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | N/A | blank | wall
217 | visual inspection for metal skeleton | track for stud installation | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | N/A | blank | wall
218 | visual inspection for metal skeleton | noggins and braces for reinforced stud support | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | N/A | blank | wall
219 | visual inspection for metal skeleton | channel | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | N/A | blank | wall
230 | visual inspection for galvanized steel channel posts for frame to lead lined doors | galvanized steel channel posts | galvanized steel channel posts for frame to lead lined doors | each batch | N/A | blank | wall
231 | visual inspection for galvanized steel channel posts for frame to lead lined doors | lead lined doors | galvanized steel channel posts for frame to lead lined doors | each batch | N/A | blank | wall

## 9
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
225 | thickness check for metal skeleton | stud | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | digital vernier scale | blank | wall
226 | thickness check for metal skeleton | channel | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | digital vernier scale | blank | wall
227 | thickness check for metal skeleton | runners | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | digital vernier scale | blank | wall
228 | thickness check for metal skeleton | track for stud installation | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | digital vernier scale | blank | wall
229 | thickness check for metal skeleton | noggins and braces for reinforced stud support | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | digital vernier scale | blank | wall
234 | thickness check for galvanized steel channel posts for frame to lead lined doors | galvanized steel channel posts | galvanized steel channel posts for frame to lead lined doors | each batch | digital vernier scale | blank | wall

## 10
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
235 | brand name check for rockwool delivered to site | mineral wool insulation | rockwool delivered to site | each batch | bill of materials | blank | wall
236 | brand name check for rockwool delivered to site | rockwool | rockwool delivered to site | each batch | bill of materials | blank | wall

## 11
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
220 | measure dimension for metal skeleton | stud | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | tape measure | blank | wall
221 | measure dimension for metal skeleton | runners | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | tape measure | blank | wall
222 | measure dimension for metal skeleton | track for stud installation | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | tape measure | blank | wall
223 | measure dimension for metal skeleton | noggins and braces for reinforced stud support | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | tape measure | blank | wall
224 | measure dimension for metal skeleton | channel | metal skeleton- studs, runners, track,channel, noggins and braces | each batch | tape measure | blank | wall
232 | measure dimension for galvanized steel channel posts for frame to lead lined doors | galvanized steel channel posts | galvanized steel channel posts for frame to lead lined doors | each batch | tape measure | blank | wall
233 | measure dimension for galvanized steel channel posts for frame to lead lined doors | lead lined doors | galvanized steel channel posts for frame to lead lined doors | each batch | tape measure | blank | wall
237 | thickness check for rockwool delivered to site | mineral wool insulation | rockwool delivered to site | each batch | tape measure | blank | wall
238 | thickness check for rockwool delivered to site | rockwool | rockwool delivered to site | each batch | tape measure | blank | wall
239 | size check for rockwool delivered to site | mineral wool insulation | rockwool delivered to site | each batch | tape measure | blank | wall
240 | size check for rockwool delivered to site | rockwool | rockwool delivered to site | each batch | tape measure | blank | wall

## 12
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
212 | internal dimension check for installation of gypsum board at wall surface | finishings | installation of gypsum board at wall surface | routine | tape measure | blank | wall
213 | internal dimension check for installation of gypsum board at wall surface | laminate for wall finsishes/laminate | installation of gypsum board at wall surface | routine | tape measure | blank | wall
214 | internal dimension check for installation of gypsum board at wall surface | gypsum board | installation of gypsum board at wall surface | routine | tape measure | blank | wall

## 13
| Inspection Task | Targeted/related Product | Corresponding Production Task | Frequency | Tool | Person | Production Phase
202 | visual inspection for installation of mep conduit at wall surface | conduit | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
203 | visual inspection for installation of mep conduit at wall surface | conduits and accessories | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
204 | visual inspection for installation of mep conduit at wall surface | flexible conduit belongs-to mep system | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
205 | visual inspection for installation of mep conduit at wall surface | upvc conduits and fittings | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
206 | visual inspection for installation of mep conduit at wall surface | upvc conduits | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
207 | visual inspection for installation of mep conduit at wall surface | flexible conduit | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
208 | visual inspection for installation of mep conduit at wall surface | mep conduit | installation of mep conduit inside hostel room at wall surface | routine | N/A | blank | wall
209 | visual inspection for installation of gypsum board at wall surface | finishings | installation of gypsum board at wall surface | routine | N/A | blank | wall
210 | visual inspection for installation of gypsum board at wall surface | laminate for wall finsishes/laminate | installation of gypsum board at wall surface | routine | N/A | blank | wall
211 | visual inspection for installation of gypsum board at wall surface | gypsum board | installation of gypsum board at wall surface | routine | N/A | blank | wall